Plan week by week

About 13 weeks remained to finish the report

Note: √ means finished

|  |  |
| --- | --- |
| Week | Workload |
| 1 | 1. The brief description of techniques applied (ML methods); √ 2. The basic description of dataset; √ 3. Read at least 3 papers and write summary; √ |
| 2 | 1. Apply techniques on dataset and interpret the result (figure out patterns), the methodology part will be described in detail; 2. Explore ways to virtualize the result; 3. The analysis of dataset; 4. 5 papers and summary |
| 3 | 1. Combine the trajectory patterns with contact information; 2. Extend methodology and result part;   OR |
| 4 | 1. Collate and polish the finished part (introduction, methodology, dataset) 2. Re-organize the finished part, make it more reasonable; 3. 5 papers and summary |
| 5 | 1. Finish the result part 2. 2 papers and summary |
| 6 | 1. Finish the discussion part 2. 2 papers and summary |
| 7 | 1. Finish the conclusion and abstract 2. 3 papers and summary |
| 8 | 1. Give the integrated literature review 2. 6 papers |
| 9 | Polish the report |
| 10 | Polish the report |
| 11 | Polish the report |
| 12 | Polish the report |
| 13 | Polish the report and submit |