Plan week by week

About 13 weeks remained to finish the report

|  |  |
| --- | --- |
| Week | Workload |
| 1 | 1. The description of techniques applied (ML methods); 2. Virtualize and interpret the results of the implemented methods 3. Read at least 4 papers and write summary; |
| 2 | 1. Apply more techniques on dataset and interpret the result; 2. 5 papers and summary |
| 3 | 1. The description of techniques applied to analyze the dataset (methodology part finished); 2. The interpretation of the dataset based on the result of 1 (dataset part finished); 3. 3 papers and summary |
| 4 | 1. Collate and polish the finished part (introduction, methodology, dataset) 2. 5 papers and summary |
| 5 | 1. Finish the result part 2. 2 papers and summary |
| 6 | 1. Finish the discussion part 2. 2 papers and summary |
| 7 | 1. Finish the conclusion and abstract 2. 3 papers and summary |
| 8 | 1. Give the integrated literature review 2. 6 papers |
| 9 | Polish the report |
| 10 | Polish the report |
| 11 | Polish the report |
| 12 | Polish the report |
| 13 | Polish the report and submit |